{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["3月份贴样计划表"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"3月份贴样计划表","index":0,"n_rows":37,"n_cols":14,"rows_kept":37,"cut":false,"hidden":false,"merged":[[0,0,0,5],[0,6,0,8],[0,9,0,12]]}
["贴样需求",{"$nulls":5},"状态",null,null,"必备资料",null,null,null,"备注"]
["日期","型号","类型","数量(套)","项目","硬件","状态","方式","预期","BOM","贴片图","钢网","回料日期"]
["2025-03-17","EB7034PS","耳机板",10,"孙慧","黄利荣","贴好","手贴","2025-03-17","√","√","√"]
["2025-03-17","RT102","耳机板",10,"蔡青莲","林工","贴好","手贴","2025-03-17","√","√","√","2025-03-20"]
["2025-03-17","OWS1020","仓板",10,"肖鹏","黄利荣","贴好","手贴","2025-03-17","√","√","√"]
["2025-03-17","OWS101","仓板",10,"肖鹏","黄利荣","贴好","手贴","2025-03-17","√","√","√"]
["2025-03-17","G39-B","仓板",10,"肖鹏",null,"贴好","手贴","2025-03-17","√","√","√","2025-03-17"]
["2025-03-17","I6","耳机+仓板",10,"朱福秀","黄伟雄","贴好","手贴","2025-03-17","√","√","√"]
["2025-03-17","GW63","仓板",10,"肖鹏","李工","贴好","手贴","2025-03-17","√","√","√"]
["2025-03-17","OWS16","耳机+仓板",10,"蔡青莲",null,"贴好","手贴","2025-03-17","√","√","√"]
["2025-03-17","HE090A","仓板",10,"蔡青莲",null,"贴好","手贴","2025-03-17","√","√","√"]
["2025-03-17","RT108","耳机板",10,"蔡青莲",null,"贴好","手贴","2025-03-17","√","√","√","2025-03-20"]
["2025-03-17","RS33","耳机板",10,"蔡青莲","卢工","贴好","手贴","2025-03-17","√","√","√","2025-03-17"]
["2025-03-17","TWS2118","耳机板",10,"蔡青莲",null,"贴好","手贴","2025-03-17","√","√","√"]
["2025-03-18","A35","耳机板",10,"肖鹏",null,"待贴样",null,"2025-03-20","√","√","√"]
["2025-03-18","E075B","耳机+仓板",10,"肖鹏",null,"贴好",null,"2025-03-20","√","√","√"]
["2025-03-18","L296","耳机板",10,"肖鹏","冯工","贴好",null,"2025-03-20","√","√","√"]
["2025-03-18","L298","耳机板",10,"肖鹏","冯工","贴好",null,"2025-03-20","√","√","√"]
["2025-03-18","RT76-8932F","耳机板",10,"蔡青莲",null,"待贴样",null,"2025-03-20","√","√","√"]
["2025-03-18","G50","耳机板",10,"肖鹏",null,"贴好",null,"2025-03-20","√","√","√"]
["2025-03-18","S5199","耳机+仓板",10,"孙慧","黄利荣","贴好",null,"2025-03-20","√","√","√"]
["2025-03-19","OWS1013","耳机板",10,"肖鹏",null,"待贴样",null,"2025-03-21","×","×","×"]
["2025-03-19","OWS620","仓板",10,"肖鹏","丁阳","待贴样",null,"2025-03-21","√","√","√"]
["2025-03-19","MK031","耳机板",10,"肖鹏",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-19","TW969","仓板",10,"肖鹏",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-19","I9","耳机+仓板",10,"朱福秀","黄伟雄","待贴样",null,"2025-03-21","√","√","√"]
["2025-03-19","BTW73","耳机板",10,"梁建庆",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","ME-889","仓板",10,"朱福秀",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","MX-OWS-06","仓板",10,"李丹",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","ME-815","耳机+仓板",10,"朱福秀",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","LP19","耳机+仓板",10,"朱福秀",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","A34","仓板",10,"肖鹏",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","A13","仓板",10,"肖鹏",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20",9011,"耳机+仓板",10,"蔡青莲",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","RS28","耳机板",10,"蔡青莲",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","RT83","耳机板",10,"蔡青莲",null,"待贴样",null,"2025-03-21","√","√","√"]
["2025-03-20","OWS1013","仓板",10,"肖鹏",null,"待贴样",null,"2025-03-21","√","√","√"]